## Sprint Planning Table
Sprint Planning Table
Sprint No. | Epic | User Story ID | User Story Description | Priority | Story Points | Acceptance Criteria (Summary)
Sprint 1 | E1 – Authentication & Role Management | US1.1 | As an Admin, I can register and log in securely so I can access the system. | High | 5 | Login, Register, JWT auth working.
|  | US1.2 | As an Admin, I can manage user roles (Admin, Staff, Guard) to control access. | High | 8 | Role-based access control applied in backend.
|  | US1.3 | As an Admin, I can view the user list with pagination. | Medium | 3 | User list loads correctly from API.
| E2 – Parking Lot Setup | US2.1 | As an Admin, I can create, update, delete parking zones and slots. | High | 8 | CRUD parking lot + slot association works.
|  | US2.2 | As an Admin, I can upload an image/layout for each parking lot. | Medium | 3 | Upload via form, image stored locally.
Sprint 2 | E3 – Vehicle Entry & Exit | US3.1 | As a Guard, I can register vehicle entry and capture plate number. | High | 8 | Entry record stored, linked to plate image.
|  | US3.2 | As a Guard, I can mark vehicle exit and calculate parking duration. | High | 5 | Exit time saved, duration auto-calculated.
|  | US3.3 | As a System, I auto-assign available parking slot to incoming vehicle. | Medium | 5 | Slot assigned dynamically based on availability.
| E4 – Payment & Ticketing | US4.1 | As a Guard, I can generate a ticket for each parked vehicle. | Medium | 3 | Ticket generated with timestamp + vehicle ID.
|  | US4.2 | As a System, I can auto-calculate parking fee upon exit. | High | 5 | Fee calculated based on duration + rates.
Sprint 3 | E5 – Reporting & Dashboard | US5.1 | As an Admin, I can view daily/weekly/monthly parking statistics. | Medium | 8 | Chart & report endpoints ready.
|  | US5.2 | As an Admin, I can export parking data as CSV/PDF. | Medium | 5 | Export endpoints working.
|  | US5.3 | As a Guard, I can view real-time available slot count. | High | 5 | Dashboard auto-updates slot usage.
| E6 – System Configuration | US6.1 | As an Admin, I can configure parking rates and time rules. | Medium | 5 | Rates editable from settings UI.
|  | US6.2 | As an Admin, I can manage company and staff info. | Low | 3 | CRUD staff + company info done.
Sprint 4 | E7 – Notifications & Logging | US7.1 | As an Admin, I can receive alert when parking lot is full. | Medium | 5 | Notification triggers at threshold.
|  | US7.2 | As a System, I log all vehicle entries/exits for audit trail. | High | 5 | Logs saved in DB + accessible in admin panel.
|  | US7.3 | As a Guard, I can view recent activity logs. | Low | 3 | Log list page visible + filterable.
| E8 – System Optimization & Deployment | US8.1 | As a DevOps, I can deploy system via CI/CD pipeline to VPS. | High | 8 | CI/CD auto-deploys on merge.
|  | US8.2 | As a Developer, I can run automated tests for APIs. | Medium | 5 | Tests pass in CI pipeline.
|  | US8.3 | As a User, I experience fast page load (<2s). | Medium | 5 | Optimize queries + cache static assets.

## Sprint 1
Task Name | User Story | Goal | Technical Details / UI | Acceptance Criteria (AC) | Sub-tasks | Story Points | Labels
[BE] - Implement User Registration API | US1.1 | Enable Admin registration securely | REST endpoint /api/auth/register; validate input; hash passwords; save to users table | [ ] Given valid info, account created [ ] Invalid info returns error [ ] Password stored hashed | [QA] - Write Registration API Unit Tests [BE] - Integrate Database Schema | 5 | backend, auth, registration, api
[BE] - Implement JWT Authentication | US1.1 | Secure login & protected routes | REST endpoint /api/auth/login; validate credentials; generate JWT; middleware to protect routes | [ ] Valid credentials return JWT [ ] Invalid credentials return error [ ] Protected routes require JWT | [QA] - JWT Auth Tests | 4 | backend, auth, jwt, security
[FE] - Registration & Login UI | US1.1 | Build responsive forms for registration/login | Registration: Name, email, phone, password, role selection; Login: Email/phone + password; input validation | [ ] Forms validate inputs [ ] Successful API calls [ ] Error messages shown correctly | N/A | 4 | frontend, auth, ui
[BE] - Role CRUD API | US1.2 | Enable Admin to manage roles | /api/roles endpoints; roles table with permissions; link role_id to users | [ ] Admin can create/update/delete roles [ ] Assign roles to users [ ] Access control enforced | [QA] - Test Role CRUD API | 8 | backend, roles, access-control
[FE] - Role Management UI | US1.2 | UI for managing user roles | Table view of roles; Add/Edit/Delete buttons; modal forms | [ ] Roles displayed correctly [ ] Admin can Add/Edit/Delete | N/A | 5 | frontend, roles, ui
[BE] - User List API | US1.3 | Paginated user list for Admin | /api/users?page=1&limit=20; return id, name, email, role | [ ] Returns paginated list [ ] Filter by role works | [QA] - User List API Tests | 3 | backend, users, pagination
[FE] - User List UI | US1.3 | Table/grid view for users | Display table with pagination controls, role filter dropdown | [ ] Table shows correct data [ ] Pagination works [ ] Filtering updates table | N/A | 3 | frontend, users, ui
[BE] - Parking Zone CRUD API | US2.1 | Enable Admin to create/update/delete zones | /api/parking/zones endpoints; store in DB with unique IDs | [ ] Admin can create/update/delete zones | [QA] - Parking Zone API Tests | 5 | backend, parking, api
[BE] - Parking Slot CRUD API | US2.1 | Manage parking slots linked to zones | /api/parking/slots endpoints; manage availability | [ ] Slots can be added/edited/deleted [ ] Availability correct | [QA] - Parking Slot API Tests | 5 | backend, parking, api
[FE] - Parking Zone & Slot UI | US2.1 | Admin panel to manage zones/slots | Table/grid UI with Add/Edit/Delete buttons; integrate API | [ ] Admin can manage zones and slots [ ] Changes trigger API | N/A | 4 | frontend, parking, ui
[BE] - Image Upload API | US2.2 | Upload parking lot images | REST endpoint to upload images; store locally; associate with zone in DB | [ ] Image uploaded successfully [ ] File path stored in DB | [QA] - Image Upload API Tests | 3 | backend, parking, image-upload
[FE] - Image Upload UI | US2.2 | Admin UI to upload/preview images | Image select, preview, upload button | [ ] Admin can select/upload image [ ] Preview displays correctly | N/A | 3 | frontend, parking, ui

## Sprint 2
Task Name | User Story | Goal | Technical Details / UI | Acceptance Criteria (AC) | Sub-tasks | Story Points | Labels
[BE] - Vehicle Entry API | US3.1 | Allow Guard to register vehicle entry | /api/vehicles/entry; store plate number, timestamp, optional image; link to slot | [ ] Entry recorded in DB [ ] Plate number saved correctly [ ] Image stored and linked | [QA] - Test Vehicle Entry API | 5 | backend, vehicle, api
[FE] - Vehicle Entry UI | US3.1 | UI for guard to register entry | Form with plate input, image upload, submit button | [ ] Guard can input plate [ ] Image upload works [ ] Submission triggers API call | N/A | 3 | frontend, vehicle, ui
[BE] - Vehicle Exit API | US3.2 | Enable Guard to register vehicle exit and calculate duration | /api/vehicles/exit; calculate duration based on entry timestamp; update DB | [ ] Exit timestamp saved [ ] Duration calculated correctly [ ] Slot marked as available | [QA] - Test Vehicle Exit API | 5 | backend, vehicle, api
[FE] - Vehicle Exit UI | US3.2 | UI for Guard to mark vehicle exit | Input plate number, show entry info, confirm exit | [ ] Guard can see entry details [ ] Exit submission triggers API [ ] Duration displayed | N/A | 3 | frontend, vehicle, ui
[BE] - Auto-Assign Parking Slot Logic | US3.3 | Auto-assign slot to incoming vehicle | Algorithm checks zone availability; max 3 vehicles per slot; return assigned slot | [ ] System assigns available slot automatically [ ] Slot availability updated | [QA] - Test Auto-Assign Logic | 5 | backend, vehicle, logic
[BE] - Ticket Generation API | US4.1 | Generate parking ticket for each vehicle | /api/tickets; include vehicle ID, timestamp, slot info | [ ] Ticket created upon vehicle entry [ ] Ticket info correct | [QA] - Test Ticket Generation API | 3 | backend, ticket, api
[FE] - Ticket UI | US4.1 | Display ticket for Guard | UI to show ticket details, print/download option | [ ] Ticket displayed correctly [ ] Print/download works | N/A | 2 | frontend, ticket, ui
[BE] - Parking Fee Calculation API | US4.2 | Auto-calculate fee on vehicle exit | Use entry/exit timestamps; configurable rates; store fee in DB | [ ] Fee calculated correctly [ ] Fee saved in DB [ ] API returns correct total | [QA] - Test Fee Calculation API | 5 | backend, payment, api
[FE] - Display Parking Fee UI | US4.2 | Show calculated fee to Guard | Show fee before confirming exit; integrate API | [ ] Fee displayed accurately [ ] Exit confirmation works | N/A | 3 | frontend, payment, ui

## Sprint 3
Task Name | User Story | Goal | Technical Details / UI | Acceptance Criteria (AC) | Sub-tasks | Story Points | Labels
[BE] - Parking Statistics API | US5.1 | Allow Admin to view daily/weekly/monthly parking statistics | /api/reports/parking?period=daily/weekly/monthly; aggregate vehicle entries/exits, slot usage, revenue | [ ] API returns correct stats for selected period [ ] Data includes number of entries/exits, occupancy, revenue | [QA] - Test Parking Statistics API | 5 | backend, reporting, api
[FE] - Statistics Dashboard UI | US5.1 | Display parking statistics visually | Charts (bar/line), filters by period, color-coded occupancy | [ ] Dashboard shows correct stats [ ] Filters update charts correctly | N/A | 3 | frontend, reporting, ui
[BE] - Export Data API | US5.2 | Allow Admin to export parking data | /api/reports/export?format=csv/pdf; include vehicle, slot, timestamps | [ ] Admin can export data in CSV and PDF [ ] Export contains correct records | [QA] - Test Data Export API | 5 | backend, reporting, export
[FE] - Export UI | US5.2 | UI to export parking data | Button/dropdown for CSV/PDF; confirmation message | [ ] Export buttons trigger correct API [ ] Download works | N/A | 2 | frontend, reporting, ui
[BE] - Real-Time Slot Count API | US5.3 | Show real-time available parking slots | /api/slots/availability; update via WebSocket or polling every 5s | [ ] API returns current slot availability [ ] Updates dynamically | [QA] - Test Real-Time Slot Count | 3 | backend, slots, real-time
[FE] - Real-Time Slot Dashboard UI | US5.3 | UI for Guard to view available slots | Live-updating counters, color-coded availability | [ ] Slot count updates in real-time [ ] Correct color indicators | N/A | 2 | frontend, slots, ui
[BE] - Parking Rate Configuration API | US6.1 | Enable Admin to configure rates and time rules | /api/config/rates; store in DB; validate rules | [ ] Admin can add/edit/delete rate rules [ ] Rules stored correctly | [QA] - Test Rate Config API | 3 | backend, config, api
[FE] - Rate Config UI | US6.1 | UI to manage parking rates | Form with rate, duration, zone selection | [ ] Admin can configure rates via UI [ ] Changes trigger API successfully | N/A | 2 | frontend, config, ui
[BE] - Staff & Company Info API | US6.2 | Manage company and staff info | CRUD endpoints /api/staff and /api/company | [ ] Admin can create/update/delete staff [ ] Company info editable | [QA] - Test Staff & Company API | 2 | backend, staff, company
[FE] - Staff & Company UI | US6.2 | UI to manage staff/company | Tables/forms for staff list and company info | [ ] CRUD operations work via UI [ ] Validation works | N/A | 1 | frontend, staff, ui

## Sprint 4
Task Name | User Story | Goal | Technical Details / UI | Acceptance Criteria (AC) | Sub-tasks | Story Points | Labels
[BE] - Full Parking Lot Notification API | US7.1 | Alert Admin when parking lot is full | /api/notifications/full-lot; trigger when occupied slots = max; send email/notification | [ ] Notification triggered at threshold [ ] Admin receives alert correctly | [QA] - Test Full Lot Notification | 3 | backend, notifications, alert
[FE] - Full Parking Lot Notification UI | US7.1 | UI to display alerts | Banner/modal on admin dashboard | [ ] Admin sees notification in dashboard [ ] Alert disappears after acknowledgement | N/A | 2 | frontend, notifications, ui
[BE] - Vehicle Entry/Exit Logging API | US7.2 | Log all entries/exits for audit | /api/logs/vehicles; store timestamp, plate, slot, action, user | [ ] All vehicle entries/exits logged [ ] Data accessible for admin | [QA] - Test Logging API | 3 | backend, logs, audit
[FE] - Logs Dashboard UI | US7.2 | Admin UI to view logs | Table with filters (date, user, action); pagination | [ ] Admin can view logs [ ] Filters and pagination work | N/A | 2 | frontend, logs, ui
[FE] - Recent Activity UI for Guard | US7.3 | Show Guard recent activities | Table/list of recent entries/exits; filter by time | [ ] Guard sees last N activities [ ] Filtering works | N/A | 2 | frontend, logs, ui
[DevOps] - CI/CD Pipeline Setup | US8.1 | Deploy system via CI/CD to VPS | Use GitHub Actions or GitLab CI; automate build, test, deployment; target VPS (157.66.26.11) | [ ] Push to main triggers pipeline [ ] Successful build and deployment to VPS | [QA] - Verify Deployment | 8 | devops, ci/cd, deployment
[QA] - Automated API Tests | US8.2 | Run automated tests for APIs | Write integration/unit tests; integrate into CI/CD pipeline | [ ] Tests pass on pipeline [ ] Failures block deployment | N/A | 5 | backend, testing, ci
[BE] - System Optimization for Performance | US8.3 | Ensure fast page load (<2s) | Optimize queries, implement caching, compress static assets | [ ] Page load <2s [ ] No functionality broken after optimization | [QA] - Performance Tests | 5 | backend, performance, optimization
[FE] - Frontend Optimization | US8.3 | Reduce page load and render time | Lazy-load components, minify assets, cache images | [ ] Page load <2s [ ] UI works correctly | [QA] - Frontend Perf Tests | 3 | frontend, performance, optimization